## Instructions
Helonix Water Tank Controller WT1.1 – Test Matrix v1.0
Date 26-09-2026. Firmware: STM32 branch fix/testing-report-24-09-26; ESP-01 web app branch fix/device-sync. Rules are described in WT1.1_Functional_Specification_v1.0.docx.
Sheet | Purpose
Test Cases | One row per test. Each test is linked to a rule ID of the specification.
Summary | Pass / Fail count per module (calculated automatically from the Status column).
Rules | All rules with a Client OK? dropdown and a Client Comment column.
Decisions | Open points that need a client decision.
Columns to fill (yellow) | Actual Result, Status, Tested By, Date, Client Comment. Developer Remark is filled by the development team.
Status values | Not Run = not tested yet Pass = result matches Expected Fail = result differs (describe it in Actual Result) Blocked = could not be tested (say why in Actual Result)
New problem found? | Add a new row at the bottom with the next Test ID and the rule ID it belongs to (or 'NEW' if no rule covers it). A 'NEW' row means the specification needs a new rule.
Example of a filled row
Test ID | TC-AUTO-07
Rule ID | AUTO-04
Precondition | Auto stopped at 100%
Steps / Event | Lower level to 25%
Expected Result | Motor ON
Actual Result | Motor ON after about 6 s
Status | Pass
Tested By | R. Kumar
Date | 27-09-2026
Client Comment | OK
Developer Remark

## Summary
Test summary
Calculated from the Status column of the Test Cases sheet.
Module | Total | Pass | Fail | Blocked | Not Run | % Pass
General behaviour
Device buttons
Auto mode
Manual mode
Timer mode
Twist mode
Semi-Auto mode
Countdown mode
Refill
Protections
Power restore
Buzzer
Display
Factory reset
Web app (ESP-01)
Total

## Rules
Rule ID | Module | Rule | Client OK? | Client Comment
GEN-01 | General behaviour | Tank level comes from the 4 level probes; a new level is accepted only after it is stable for 5 s.
GEN-02 | General behaviour | If a wireless tank transmitter is paired, its level is used; during a signal gap the last received level is kept.
GEN-03 | General behaviour | After power-up the motor never starts during the first 10 s.
GEN-04 | General behaviour | A ground water change (YES/NO) is accepted only after it has lasted 10 s.
GEN-05 | General behaviour | All settings (limits, timer slots, twist, buzzer, countdown time, power restore, last mode) are kept through power cuts and firmware updates.
GEN-06 | General behaviour | The clock keeps running during a power cut on its backup battery, and is not changed by firmware updates.
GEN-07 | General behaviour | Relay 2 gives a 2 s pulse when the motor starts and relay 3 a 2 s pulse when it stops (for an external starter panel).
BTN-01 | Device buttons | Button 1 short press: Refill start / stop. Long press: Manual on / off.
BTN-02 | Device buttons | Button 2 short press: Auto on / Auto off (motor off). Long press: open the menu.
BTN-03 | Device buttons | Button 3 short press: Timer mode on / off. Long press: Semi-Auto on / off.
BTN-04 | Device buttons | Button 4 short press: Countdown start (saved time) / stop. Long press: edit the countdown time.
BTN-05 | Device buttons | Twist mode is started and stopped from Menu > Twist Mode or from the app.
BTN-06 | Device buttons | Quick taps are always registered; in menus and edit screens holding Up/Down repeats the step and speeds up after 3 s. On the dashboard holding a button never acts as repeated short presses.
AUTO-01 | Auto mode | Auto is started with button 2 or from the app.
AUTO-02 | Auto mode | When no mode is running and the level falls to 50%, the device starts Auto by itself - unless the user switched Auto off.
AUTO-03 | Auto mode | Motor ON when the level is at or below 50% (first start).
AUTO-04 | Auto mode | After Auto has filled the tank, the motor starts again only when the level is at or below 25% (stays off at 75% and 50%).
AUTO-05 | Auto mode | Motor OFF when the tank is full (100%).
AUTO-06 | Auto mode | Ground water detected (NO to YES): motor ON if the level is at or below 75%.
AUTO-07 | Auto mode | Ground water lost (YES to NO) while running: motor OFF, then waits the testing gap.
AUTO-08 | Auto mode | Dry run enabled: after the dry run time the sensor is checked; water found - motor keeps running until the tank is full.
AUTO-09 | Auto mode | Dry run enabled, no water: motor OFF, waits the testing gap, then tries again.
AUTO-10 | Auto mode | After the retry count is used up, the motor waits for the next on key (ground water detected, or the user).
AUTO-11 | Auto mode | Button 2 while Auto is running: motor OFF, screen shows "AUTO M:OFF". This still counts as Auto for power restore.
AUTO-12 | Auto mode | Voltage, current and max run protections stop the motor (see Protections).
MAN-01 | Manual mode | Manual is started with a long press of button 1 or from the app.
MAN-02 | Manual mode | In Manual only the user (button or app) can switch the motor ON.
MAN-03 | Manual mode | Motor OFF by: user, voltage fault, over/under current, max run time, power off.
MAN-04 | Manual mode | Tank full does NOT stop the motor in Manual; the tank-full buzzer sounds for 30 s if enabled.
MAN-05 | Manual mode | Dry run and ground water are not used in Manual.
MAN-06 | Manual mode | When a protection trips, the motor stops and Manual mode ends; only the user can start it again.
TMR-01 | Timer mode | Up to 5 time slots, each with an ON time, OFF time and its own days of the week; a slot can be switched off.
TMR-02 | Timer mode | Timer is started with button 3 or from the app (Save & Start Timer).
TMR-03 | Timer mode | Motor ON when the clock enters an active slot (right time and right day).
TMR-04 | Timer mode | Motor OFF at the slot's OFF time.
TMR-05 | Timer mode | Outside every slot the motor stays OFF; ground water and dry run are ignored.
TMR-06 | Timer mode | Inside a slot, ground water detected: motor ON.
TMR-07 | Timer mode | Inside a slot, ground water lost: motor OFF, then waits the testing gap.
TMR-08 | Timer mode | Dry run enabled: same test / testing gap / retry count as Auto.
TMR-09 | Timer mode | While running, if the dry run sensor shows no water, the motor stops and waits the testing gap.
TMR-10 | Timer mode | Tank full: motor OFF; it starts again as soon as the level drops below 100% while the slot is active (see decision DEC-01).
TMR-11 | Timer mode | A slot switched off in the app or on the device stays off after saving and after a reboot.
TWS-01 | Twist mode | Twist is started / stopped from Menu > Twist Mode or from the app. Settings: ON duration, OFF duration (minutes), optional start and stop time.
TWS-02 | Twist mode | ON period: motor ON for the ON duration. OFF period: motor OFF for the OFF duration. Then repeats.
TWS-03 | Twist mode | Twist runs only between its start and stop time; if both are equal it runs all day.
TWS-04 | Twist mode | Dry run enabled: tested at the start of every ON period; water found - motor runs the rest of the ON period.
TWS-05 | Twist mode | Dry run enabled, no water: motor OFF for the rest of that ON period; the OFF period follows and the next ON period tests again. Twist does not stop.
TWS-06 | Twist mode | If the ON duration is shorter than the dry run time, the check is made at the end of the ON period.
TWS-07 | Twist mode | Ground water lost (YES to NO): motor OFF until ground water returns, then a new ON period starts.
TWS-08 | Twist mode | If the ground water probe is not fitted (always NO), Twist ignores it.
TWS-09 | Twist mode | Tank full: motor OFF; Twist restarts (with an ON period) only when the level is at or below 25%.
TWS-10 | Twist mode | Twist settings are saved and kept after a reboot.
SEMI-01 | Semi-Auto mode | Semi-Auto is started with a long press of button 3 or from the app; it is a single run to fill the tank.
SEMI-02 | Semi-Auto mode | Motor ON when Semi-Auto starts.
SEMI-03 | Semi-Auto mode | Tank full: motor OFF and does not restart by itself.
SEMI-04 | Semi-Auto mode | Dry run enabled, no water after the dry run time: motor OFF and Semi-Auto ends.
SEMI-05 | Semi-Auto mode | Protections stop the motor; max run time ends Semi-Auto.
CD-01 | Countdown mode | Countdown runs the motor for a set time (1-180 min, default 10 min); started with button 4 or from the app.
CD-02 | Countdown mode | Motor OFF when the time ends or the user stops it (button 4 or app). However the countdown ends, the mode that was running before it (e.g. Auto, Timer, Twist, Manual, or Auto switched off with button 2) continues and is shown on the screen.
CD-08 | Countdown mode | While a countdown runs, the screen always shows the time left - also when it was started from the app or resumed after a power cut.
CD-03 | Countdown mode | Tank full: motor OFF and stays off until the time ends.
CD-04 | Countdown mode | The time is set with a long press of button 4 (Down +1, Up -1, Select). It is saved and used by every later button 4 press; a time set in the app is also saved as the button time.
CD-05 | Countdown mode | Dry run enabled, no water after the dry run time: Countdown ends.
CD-06 | Countdown mode | Voltage and current faults end the Countdown. Max run time does not apply.
CD-07 | Countdown mode | Power restore ON: a countdown running at power loss continues with the time it had left (saved every minute, so up to 1 min may be repeated). When it ends, the mode that was running before it continues - this is also kept in memory.
REF-01 | Refill | Refill is started with a short press of button 1 or from the app; it is not started if the tank is already full.
REF-02 | Refill | Tank full: Refill ends and the previous mode (e.g. Auto) continues.
REF-03 | Refill | Refill is stopped by the user (button 1), max run time or protections.
REF-04 | Refill | Dry run enabled, no water: Refill ends and the previous mode continues.
PRT-01 | Protections | Low / high voltage (default 180 V / 280 V): voltage outside the limits for 3 s stops the motor; it is checked all the time, so a bad supply also prevents a start. Recovers after 10 s back in range; Manual ends.
PRT-02 | Protections | Over-load current (default 25 A): above the limit for 3 s stops the motor; the first 3 s after a start are ignored. Motor may restart after the testing gap; Manual ends.
PRT-03 | Protections | Under-load current (default off): below the limit for 3 s stops the motor; restart after the testing gap; Manual ends.
PRT-04 | Protections | Max run time (default 150 min): after running this long the motor stops. Manual, Semi-Auto and Refill end; Auto, Timer and Twist may run again after the testing gap; not applied to Countdown.
PRT-05 | Protections | A limit of 0 (or switched off in the app) disables that protection.
PRT-06 | Protections | Voltage and current can be calibrated from the app against a meter reading; with no load the current shows 0.0 A.
PWR-01 | Power restore | Device Setup > PwrRestore has two values: ON and OFF (factory default OFF).
PWR-02 | Power restore | ON, last mode Auto (motor ON, or switched off with button 2): after power returns - Auto, motor ON after 10 s; stays OFF if the tank is full.
PWR-03 | Power restore | ON, last mode Manual: Manual, motor OFF (one long press of button 1 starts it).
PWR-04 | Power restore | ON, last mode Timer: Timer; motor runs again if it was running and the slot is still active.
PWR-05 | Power restore | ON, last mode Twist: Twist continues with an ON period if the motor was running, else with an OFF period.
PWR-06 | Power restore | ON, last mode Semi-Auto / Refill: not restored (one-time runs). Countdown: continues with the time it had left (see CD-07).
PWR-07 | Power restore | OFF: after power returns always Manual, motor OFF.
BUZ-01 | Buzzer | Pump on: beeps once per second while the motor runs (if enabled).
BUZ-02 | Buzzer | Tank full: buzzer for 30 s (if enabled).
BUZ-03 | Buzzer | Tank empty (level reaches 0%): buzzer for 15 s (if enabled).
BUZ-04 | Buzzer | Each buzzer can be switched on/off separately; all are off by default.
DSP-01 | Display | Line 1: mode, motor state and level, e.g. "AUTO M:ON 50%".
DSP-02 | Display | Line 2: G.W:YES/NO, "DRY" when the dry run sensor shows no water, and the time; "TANK FULL" when full.
DSP-03 | Display | Page 2: voltage, current and day, or the active fault (voltage / overload / underload error).
FAC-01 | Factory reset | Factory reset (menu or app) sets: dry run disabled (2 min), testing gap 30 min, max run 150 min, retry count 5, low/high voltage 180/280 V, over-load 25 A, under-load disabled, power restore OFF, buzzer all off, countdown 10 min, timer slots and twist cleared.
APP-01 | Web app (ESP-01) | Every app page (settings, timer, twist, countdown) shows the values currently stored on the device, not app defaults.
APP-02 | Web app (ESP-01) | If the device does not answer, the page says so and shows the last known values.
APP-03 | Web app (ESP-01) | Apply Settings saves on the device and the page reloads the values the device confirmed.
APP-04 | Web app (ESP-01) | Status (motor, level, mode) updates within about 3 s.
APP-05 | Web app (ESP-01) | Timer page sends all 5 slots; has Save & Start and Stop Timer.
APP-06 | Web app (ESP-01) | Twist page shows saved settings and running state; has Save & Start and Stop Twist; durations in minutes.
APP-07 | Web app (ESP-01) | Countdown page shows a countdown that is already running on the device.
APP-08 | Web app (ESP-01) | Settings page has separate buzzer switches (pump on, tank full, tank empty), power restore ON/OFF and factory reset.

## Test Cases
Test ID | Module | Rule ID | Rule (from Rules sheet) | Precondition / setup | Steps / event | Expected result | Actual result | Status | Tested by | Date | Client Comment | Developer Remark
TC-GEN-01 | General behaviour | GEN-01 |  | Any mode, level 50% | Touch the 75% probe for 3 s only, then release | Level stays 50% (change shorter than 5 s is ignored) |  | Not Run
TC-GEN-02 | General behaviour | GEN-01 |  | Any mode, level 50% | Touch the 75% probe and hold 6 s | Level changes to 75% after about 5 s |  | Not Run
TC-GEN-03 | General behaviour | GEN-02 |  | Wireless transmitter paired and sending | Switch the transmitter off for 2 min | Level keeps the last received value; no false TANK FULL |  | Not Run
TC-GEN-04 | General behaviour | GEN-03 |  | Power restore ON, Auto, level 25% | Switch power off and on | Motor does not start before 10 s; starts after 10 s |  | Not Run
TC-GEN-05 | General behaviour | GEN-04 |  | Auto, level 60%, motor off | Connect G.W for 5 s only, then remove | No reaction (change shorter than 10 s ignored) |  | Not Run
TC-GEN-06 | General behaviour | GEN-05 |  | Change max run, voltages, buzzer, countdown time, a timer slot | Switch power off and on | All changed values are still set (device menu and app) |  | Not Run
TC-GEN-07 | General behaviour | GEN-05 |  | Settings changed | Flash new firmware | All settings kept |  | Not Run
TC-GEN-08 | General behaviour | GEN-06 |  | Clock set correctly | Power off for 10 min, then on | Clock shows the correct time and date |  | Not Run
TC-GEN-09 | General behaviour | GEN-07 |  | Starter panel (or meter) on relay 2 and 3 | Start the motor, then stop it | Relay 2 closes 2 s at start; relay 3 closes 2 s at stop |  | Not Run
TC-BTN-01 | Device buttons | BTN-01 |  | Dashboard, level 50% | Short press button 1 | Refill starts, motor ON; press again - Refill stops |  | Not Run
TC-BTN-02 | Device buttons | BTN-01 |  | Dashboard | Hold button 1 for 2 s | Manual mode, motor ON; hold again - Manual off |  | Not Run
TC-BTN-03 | Device buttons | BTN-02 |  | Dashboard | Short press button 2 | Auto on; press again - motor off, screen AUTO M:OFF |  | Not Run
TC-BTN-04 | Device buttons | BTN-02 |  | Dashboard | Hold button 2 for 2 s | Menu opens |  | Not Run
TC-BTN-05 | Device buttons | BTN-03 |  | Dashboard | Short press button 3 | Timer mode on; press again - Timer off |  | Not Run
TC-BTN-06 | Device buttons | BTN-03 |  | Dashboard | Hold button 3 for 2 s | Semi-Auto starts; hold again - Semi-Auto off |  | Not Run
TC-BTN-07 | Device buttons | BTN-04 |  | Dashboard | Short press button 4 | Countdown starts with the saved time; press again - stops |  | Not Run
TC-BTN-08 | Device buttons | BTN-04 |  | Dashboard | Hold button 4 for 2 s | Countdown edit screen opens (countdown is NOT started/stopped while holding) |  | Not Run
TC-BTN-09 | Device buttons | BTN-05 |  | Menu | Menu > Twist Mode > Select | Twist starts; repeat - Twist stops |  | Not Run
TC-BTN-10 | Device buttons | BTN-06 |  | Dashboard | Press each button very quickly (short tap) | Every tap is registered |  | Not Run
TC-BTN-11 | Device buttons | BTN-06 |  | Device Setup > High Volt edit | Hold Up for 5 s | Value steps repeatedly and speeds up after 3 s |  | Not Run
TC-AUTO-01 | Auto mode | AUTO-01 |  | No mode, level 50% | Press button 2 | Auto, motor ON |  | Not Run
TC-AUTO-02 | Auto mode | AUTO-03 |  | No mode, level 75% | Press button 2 | Auto, motor OFF (waits) |  | Not Run
TC-AUTO-03 | Auto mode | AUTO-03 |  | Auto waiting at 75% | Lower level to 50% | Motor ON |  | Not Run
TC-AUTO-04 | Auto mode | AUTO-05 |  | Auto running | Raise level to 100% | Motor OFF within about 10 s; TANK FULL shown |  | Not Run
TC-AUTO-05 | Auto mode | AUTO-04 |  | Auto stopped at 100% | Lower level to 75% | Motor stays OFF |  | Not Run
TC-AUTO-06 | Auto mode | AUTO-04 |  | Auto stopped at 100% | Lower level to 50% | Motor stays OFF |  | Not Run
TC-AUTO-07 | Auto mode | AUTO-04 |  | Auto stopped at 100% | Lower level to 25% | Motor ON |  | Not Run
TC-AUTO-08 | Auto mode | AUTO-02 |  | No mode active, level 75% | Lower level to 50%, wait | Device starts Auto by itself, motor ON |  | Not Run
TC-AUTO-09 | Auto mode | AUTO-02 |  | Auto switched off by button 2 (AUTO M:OFF), level 75% | Lower level to 50% | Auto does NOT start by itself |  | Not Run
TC-AUTO-10 | Auto mode | AUTO-08 |  | Dry run ON (2 min), dry sensor in water, level 25% | Start Auto, wait 3 min | Motor keeps running until tank full |  | Not Run
TC-AUTO-11 | Auto mode | AUTO-09 |  | Dry run ON (2 min), dry sensor dry, testing gap 5 min | Start Auto | Motor OFF after 2 min; DRY shown; retries after 5 min |  | Not Run
TC-AUTO-12 | Auto mode | AUTO-10 |  | Dry run ON, retry count 2, dry sensor dry | Start Auto, wait for 2 failed tests | Motor stays OFF; waits for G.W or user |  | Not Run
TC-AUTO-13 | Auto mode | AUTO-06 |  | Auto waiting at 60% (motor off) | Connect G.W (YES), wait 10 s | Motor ON |  | Not Run
TC-AUTO-14 | Auto mode | AUTO-06 |  | Auto waiting at 100% | Connect G.W | Motor stays OFF |  | Not Run
TC-AUTO-15 | Auto mode | AUTO-07 |  | Auto running, G.W YES | Remove G.W, wait 10 s | Motor OFF; restarts after the testing gap or when G.W returns |  | Not Run
TC-AUTO-16 | Auto mode | AUTO-07 |  | Auto stopped by G.W loss | Reconnect G.W before the testing gap ends | Motor ON after 10 s |  | Not Run
TC-AUTO-17 | Auto mode | AUTO-06 |  | G.W probe not fitted | Run Auto normally | Auto works by level only |  | Not Run
TC-AUTO-18 | Auto mode | AUTO-11 |  | Auto running | Press button 2 | Motor OFF, screen AUTO M:OFF |  | Not Run
TC-AUTO-19 | Auto mode | AUTO-12 |  | Auto running | Drop supply below low-voltage limit for 5 s | Motor OFF, VOLTERR; restarts 10 s after voltage returns |  | Not Run
TC-AUTO-20 | Auto mode | AUTO-12 |  | Auto running | Load above over-load limit | Motor OFF after 3 s; may restart after the testing gap |  | Not Run
TC-AUTO-21 | Auto mode | AUTO-12 |  | Max run 5 min, Auto running | Let it run 5 min | Motor OFF; may restart after the testing gap |  | Not Run
TC-AUTO-22 | Auto mode | AUTO-03 |  | Example 1 from report: dry run 3 min, gap 15 min, 10:00 start, no water | At 10:05 connect G.W, keep dry sensor dry | 10:03 OFF; 10:05:10 ON; 10:08 OFF; next try 10:23 |  | Not Run
TC-AUTO-23 | Auto mode | AUTO-07 |  | Example 2 from report: as above | At 10:05 connect G.W, at 10:06 remove it | 10:05:10 ON; 10:06:10 OFF; next try 10:21 |  | Not Run
TC-MAN-01 | Manual mode | MAN-01 |  | Dashboard | Hold button 1 for 2 s | Manual, motor ON |  | Not Run
TC-MAN-02 | Manual mode | MAN-02 |  | Manual running | Hold button 1 again | Motor OFF, screen MANUAL |  | Not Run
TC-MAN-03 | Manual mode | MAN-04 |  | Manual running, tank-full buzzer on | Raise level to 100% | Motor keeps running; buzzer 30 s |  | Not Run
TC-MAN-04 | Manual mode | MAN-05 |  | Manual running | Remove dry sensor and G.W | No effect on the motor |  | Not Run
TC-MAN-05 | Manual mode | MAN-06 |  | Manual running | Low voltage for 5 s | Motor OFF, Manual ends; does not restart by itself |  | Not Run
TC-MAN-06 | Manual mode | MAN-06 |  | Manual running | Over-load | Motor OFF, Manual ends |  | Not Run
TC-MAN-07 | Manual mode | MAN-03 |  | Max run 5 min, Manual running | Let it run 5 min | Motor OFF, Manual ends |  | Not Run
TC-MAN-08 | Manual mode | MAN-01 |  | App connected | App: switch motor ON, then OFF | Device follows the app |  | Not Run
TC-TMR-01 | Timer mode | TMR-03 |  | Slot 1 = now to now+10 min, today selected | Start Timer (button 3) | Motor ON |  | Not Run
TC-TMR-02 | Timer mode | TMR-04 |  | Timer running in slot 1 | Wait until the slot OFF time | Motor OFF |  | Not Run
TC-TMR-03 | Timer mode | TMR-03 |  | Slot 1 active time, today NOT selected | Start Timer | Motor stays OFF |  | Not Run
TC-TMR-04 | Timer mode | TMR-03 |  | Slot crossing midnight 23:50-00:10 | Wait through midnight | Motor ON 23:50 to 00:10 |  | Not Run
TC-TMR-05 | Timer mode | TMR-01 |  | Two slots set | Wait through both slots | Motor runs in both slots only |  | Not Run
TC-TMR-06 | Timer mode | TMR-11 |  | Slot 1 enabled | App: uncheck slot 1, save, reload page | Slot 1 shows unchecked |  | Not Run
TC-TMR-07 | Timer mode | TMR-11 |  | Slot 1 disabled | Reboot the device, open app timer page | Slot 1 still unchecked |  | Not Run
TC-TMR-08 | Timer mode | TMR-08 |  | Dry run ON, dry sensor dry, slot active | Start Timer | Motor OFF after dry run time; retries after the testing gap while the slot is active |  | Not Run
TC-TMR-09 | Timer mode | TMR-09 |  | Timer running, water confirmed | Remove water from dry sensor | Motor OFF; waits the testing gap |  | Not Run
TC-TMR-10 | Timer mode | TMR-06 |  | Slot active, motor off (after dry fail) | Connect G.W, wait 10 s | Motor ON |  | Not Run
TC-TMR-11 | Timer mode | TMR-05 |  | Outside every slot | Connect G.W | Nothing happens |  | Not Run
TC-TMR-12 | Timer mode | TMR-07 |  | Slot active, running, G.W YES | Remove G.W, wait 10 s | Motor OFF; waits the testing gap |  | Not Run
TC-TMR-13 | Timer mode | TMR-10 |  | Timer running | Raise level to 100% | Motor OFF |  | Not Run
TC-TMR-14 | Timer mode | TMR-10 |  | Timer stopped at 100%, slot active | Lower level to 75% | Motor ON (see decision DEC-01) |  | Not Run
TC-TMR-15 | Timer mode | TMR-02 |  | App connected | App: Save & Start Timer, then Stop Timer | Timer starts, then stops |  | Not Run
TC-TMR-16 | Timer mode | TMR-03 |  | Example from report: slot 10:00-11:50, dry 3 min, gap 15 min | At 15:00 connect G.W | Nothing happens (outside slot) |  | Not Run
TC-TWS-01 | Twist mode | TWS-02 |  | Twist ON 2 min, OFF 2 min, all day | Start Twist | Motor ON 2 min, OFF 2 min, repeats |  | Not Run
TC-TWS-02 | Twist mode | TWS-03 |  | Twist start/stop time outside now | Start Twist | Motor stays OFF until the start time |  | Not Run
TC-TWS-03 | Twist mode | TWS-03 |  | Twist start time = stop time | Start Twist | Runs all day |  | Not Run
TC-TWS-04 | Twist mode | TWS-04 |  | Dry run ON (1 min), dry sensor in water, ON 3 min | Start Twist | Motor runs the full 3 min ON period |  | Not Run
TC-TWS-05 | Twist mode | TWS-05 |  | Dry run ON (1 min), dry sensor dry, ON 3 min, OFF 2 min | Start Twist | ON 1 min then OFF for remaining 2 min, then 2 min OFF, next ON period tests again; Twist continues |  | Not Run
TC-TWS-06 | Twist mode | TWS-06 |  | Dry run 2 min, ON duration 1 min, dry sensor dry | Start Twist | Check made at end of the ON period; Twist continues |  | Not Run
TC-TWS-07 | Twist mode | TWS-07 |  | Twist running, G.W YES | Remove G.W, wait 10 s | Motor OFF and stays OFF |  | Not Run
TC-TWS-08 | Twist mode | TWS-07 |  | Twist held by G.W loss | Reconnect G.W, wait 10 s | New ON period starts |  | Not Run
TC-TWS-09 | Twist mode | TWS-08 |  | G.W probe not fitted | Run Twist | Normal ON/OFF cycle |  | Not Run
TC-TWS-10 | Twist mode | TWS-09 |  | Twist running | Raise level to 100% | Motor OFF |  | Not Run
TC-TWS-11 | Twist mode | TWS-09 |  | Twist stopped at 100% | Lower level to 75%, then 50% | Motor stays OFF |  | Not Run
TC-TWS-12 | Twist mode | TWS-09 |  | Twist stopped at 100% | Lower level to 25% | Twist restarts with an ON period |  | Not Run
TC-TWS-13 | Twist mode | TWS-10 |  | Twist settings set in app | Reboot, open app twist page and Menu > Twist | Same settings shown |  | Not Run
TC-TWS-14 | Twist mode | TWS-01 |  | Twist running | App: Stop Twist | Twist stops, motor OFF |  | Not Run
TC-SEMI-01 | Semi-Auto mode | SEMI-02 |  | Level 50% | Hold button 3 for 2 s | Semi-Auto, motor ON |  | Not Run
TC-SEMI-02 | Semi-Auto mode | SEMI-03 |  | Semi-Auto running | Raise level to 100%, then lower to 25% | Motor OFF at 100% and stays OFF |  | Not Run
TC-SEMI-03 | Semi-Auto mode | SEMI-04 |  | Dry run ON, dry sensor dry | Start Semi-Auto | Motor OFF after dry run time; Semi-Auto ends |  | Not Run
TC-SEMI-04 | Semi-Auto mode | SEMI-05 |  | Semi-Auto running | Over-load | Motor OFF |  | Not Run
TC-SEMI-05 | Semi-Auto mode | SEMI-05 |  | Max run 5 min | Run Semi-Auto 5 min | Motor OFF; Semi-Auto ends |  | Not Run
TC-SEMI-06 | Semi-Auto mode | SEMI-01 |  | Semi-Auto running | Hold button 3 again | Semi-Auto off, motor OFF |  | Not Run
TC-CD-01 | Countdown mode | CD-01 |  | Saved countdown time 10 min | Short press button 4 | Motor ON; countdown 10:00 shown |  | Not Run
TC-CD-02 | Countdown mode | CD-02 |  | Countdown 1 min | Wait 1 min | Motor OFF when time ends |  | Not Run
TC-CD-03 | Countdown mode | CD-02 |  | Countdown running (no mode before it) | Press button 4 | Countdown stops, motor OFF |  | Not Run
TC-CD-04 | Countdown mode | CD-02 |  | Auto running, then countdown started | Press button 4 to stop the countdown early | Back in Auto; screen shows AUTO |  | Not Run
TC-CD-05 | Countdown mode | CD-02 |  | Auto switched off with button 2 (AUTO M:OFF), then countdown 1 min | Wait until the countdown ends | Screen shows AUTO M:OFF again |  | Not Run
TC-CD-06 | Countdown mode | CD-08 |  | App connected | Start countdown 5 min from the app | Device screen shows the time left counting down |  | Not Run
TC-CD-07 | Countdown mode | CD-08 |  | PwrRestore ON, countdown running | Power off and on | After the welcome screen, the countdown screen shows the time left |  | Not Run
TC-CD-08 | Countdown mode | CD-02 |  | Auto running at 75% (motor off) | Start countdown 1 min, wait until it ends | Motor OFF at the end; device back in Auto (screen AUTO) |  | Not Run
TC-CD-09 | Countdown mode | CD-02 |  | Timer mode on | Start countdown 1 min, wait until it ends | Back in Timer mode |  | Not Run
TC-CD-10 | Countdown mode | CD-02 |  | No mode running | Start countdown 1 min, wait until it ends | Motor OFF; no mode running |  | Not Run
TC-CD-11 | Countdown mode | CD-07 |  | PwrRestore ON, Auto, then countdown 10 min started | After 4 min switch power off for 1 min, then on | Countdown continues with about 6 min left (up to 1 min extra); at the end back to Auto |  | Not Run
TC-CD-12 | Countdown mode | CD-07 |  | PwrRestore OFF, countdown running | Power off and on | Manual, motor OFF (countdown not resumed) |  | Not Run
TC-CD-13 | Countdown mode | CD-04 |  | Dashboard | Hold button 4, set 15 with Down/Up, Select | Countdown 15 min starts |  | Not Run
TC-CD-14 | Countdown mode | CD-04 |  | Countdown time set to 15 | Reboot, then short press button 4 | Countdown 15 min starts |  | Not Run
TC-CD-15 | Countdown mode | CD-04 |  | App connected | App: start countdown 20 min, stop it, then press button 4 | Button starts 20 min |  | Not Run
TC-CD-16 | Countdown mode | CD-03 |  | Countdown running | Raise level to 100% | Motor OFF, stays off until the time ends |  | Not Run
TC-CD-17 | Countdown mode | CD-05 |  | Dry run ON, dry sensor dry | Start countdown 10 min | Motor OFF after dry run time; Countdown ends |  | Not Run
TC-CD-18 | Countdown mode | CD-06 |  | Countdown running | Over-load | Motor OFF; Countdown ends |  | Not Run
TC-CD-19 | Countdown mode | CD-06 |  | Max run 5 min, countdown 10 min | Run countdown | Motor runs the full 10 min |  | Not Run
TC-REF-01 | Refill | REF-01 |  | Auto waiting at 75% | Short press button 1 | Refill, motor ON |  | Not Run
TC-REF-02 | Refill | REF-02 |  | Refill running from Auto | Raise level to 100% | Motor OFF; back to Auto |  | Not Run
TC-REF-03 | Refill | REF-03 |  | Refill running | Short press button 1 | Refill stops; previous mode |  | Not Run
TC-REF-04 | Refill | REF-01 |  | Level 100% | Short press button 1 | Refill does not start |  | Not Run
TC-REF-05 | Refill | REF-04 |  | Dry run ON, dry sensor dry | Start Refill | Refill ends after dry run time; previous mode |  | Not Run
TC-REF-06 | Refill | REF-03 |  | Max run 5 min | Run Refill 5 min | Motor OFF; Refill ends |  | Not Run
TC-PRT-01 | Protections | PRT-01 |  | Supply below low-voltage limit | Try to start any mode | Motor does not start; VOLTERR shown |  | Not Run
TC-PRT-02 | Protections | PRT-01 |  | Supply above high-voltage limit | Try to start any mode | Motor does not start; VOLTERR shown |  | Not Run
TC-PRT-03 | Protections | PRT-01 |  | Voltage fault active | Return voltage to normal | Fault clears after 10 s |  | Not Run
TC-PRT-04 | Protections | PRT-02 |  | Over-load 25 A, motor with high start current | Start motor | No trip during the first 3 s |  | Not Run
TC-PRT-05 | Protections | PRT-02 |  | Over-load set just below running current | Run motor | Motor OFF after 3 s; OVERLD shown |  | Not Run
TC-PRT-06 | Protections | PRT-03 |  | Under-load set above running current | Run motor | Motor OFF after 3 s; UNDERLD shown |  | Not Run
TC-PRT-07 | Protections | PRT-04 |  | Max run 5 min, testing gap 5 min, Auto at 25% | Let the motor run 5 min, then wait 5 min | Motor OFF after 5 min (red LED blinks); Auto may start again after the 5 min gap |  | Not Run
TC-PRT-08 | Protections | PRT-05 |  | Low voltage switched off in app | Supply below the old limit | Motor runs |  | Not Run
TC-PRT-09 | Protections | PRT-06 |  | Motor off, no load | Read current on page 2 | 0.0 A |  | Not Run
TC-PRT-10 | Protections | PRT-06 |  | Meter shows 230 V, device shows other value | App: calibrate voltage to 230 | Device shows 230 V; kept after reboot |  | Not Run
TC-PWR-01 | Power restore | PWR-02 |  | PwrRestore ON, Auto running | Power off and on | Auto; motor ON after 10 s |  | Not Run
TC-PWR-02 | Power restore | PWR-02 |  | PwrRestore ON, Auto switched off by button 2 (AUTO M:OFF) | Power off and on | Auto; motor ON after 10 s |  | Not Run
TC-PWR-03 | Power restore | PWR-02 |  | PwrRestore ON, Auto, level 100% | Power off and on | Auto; motor stays OFF |  | Not Run
TC-PWR-04 | Power restore | PWR-03 |  | PwrRestore ON, Manual running | Power off and on | Manual, motor OFF; long press button 1 starts it |  | Not Run
TC-PWR-05 | Power restore | PWR-04 |  | PwrRestore ON, Timer running in active slot | Power off and on (slot still active) | Timer; motor ON after 10 s |  | Not Run
TC-PWR-06 | Power restore | PWR-05 |  | PwrRestore ON, Twist in ON period | Power off and on | Twist continues with an ON period |  | Not Run
TC-PWR-07 | Power restore | PWR-06 |  | PwrRestore ON, Countdown running with 8 min left | Power off and on | Countdown continues with about 8 min left |  | Not Run
TC-PWR-08 | Power restore | PWR-06 |  | PwrRestore ON, Semi-Auto running | Power off and on | Semi-Auto not resumed |  | Not Run
TC-PWR-09 | Power restore | PWR-07 |  | PwrRestore OFF, Auto running | Power off and on | Manual, motor OFF |  | Not Run
TC-PWR-10 | Power restore | PWR-01 |  | PwrRestore ON | Reboot; open Device Setup and app settings | Still ON in both |  | Not Run
TC-BUZ-01 | Buzzer | BUZ-01 |  | Pump-on buzzer on | Start motor | Beeps once per second while running |  | Not Run
TC-BUZ-02 | Buzzer | BUZ-02 |  | Tank-full buzzer on | Fill tank | Buzzer 30 s |  | Not Run
TC-BUZ-03 | Buzzer | BUZ-03 |  | Tank-empty buzzer on | Lower level to 0% | Buzzer 15 s |  | Not Run
TC-BUZ-04 | Buzzer | BUZ-04 |  | All buzzers off | Run motor, fill tank, empty tank | No buzzer |  | Not Run
TC-BUZ-05 | Buzzer | BUZ-04 |  | App settings | Switch only tank-full buzzer on, apply, reload | Only tank-full shown on; only it sounds |  | Not Run
TC-DSP-01 | Display | DSP-01 |  | Auto running at 50% | Look at line 1 | AUTO M:ON 50% |  | Not Run
TC-DSP-02 | Display | DSP-02 |  | G.W connected | Look at line 2 | G.W:YES and time |  | Not Run
TC-DSP-03 | Display | DSP-02 |  | Dry sensor dry | Look at line 2 | DRY shown |  | Not Run
TC-DSP-04 | Display | DSP-02 |  | Level 100% | Look at line 2 | TANK FULL and time |  | Not Run
TC-DSP-05 | Display | DSP-03 |  | Normal | Wait for page 2 | Voltage, current and day |  | Not Run
TC-FAC-01 | Factory reset | FAC-01 |  | Settings changed | Menu > Reset To Default > YES | All values as listed in FAC-01 |  | Not Run
TC-FAC-02 | Factory reset | FAC-01 |  | App connected, settings changed | App: Factory Reset | App shows the default values |  | Not Run
TC-APP-01 | Web app (ESP-01) | APP-01 |  | Max run changed on the device menu | Open app settings page | App shows the new value |  | Not Run
TC-APP-02 | Web app (ESP-01) | APP-02 |  | Device disconnected from ESP | Open app settings page | Message: device not responding - last known values |  | Not Run
TC-APP-03 | Web app (ESP-01) | APP-03 |  | App settings | Change high voltage, Apply | Message: saved on device; page shows the new value |  | Not Run
TC-APP-04 | Web app (ESP-01) | APP-04 |  | App dashboard open | Start motor from device button | App shows motor ON within about 3 s |  | Not Run
TC-APP-05 | Web app (ESP-01) | APP-05 |  | App timer page | Enable slot 2, Save & Start | Timer starts with slot 2 |  | Not Run
TC-APP-06 | Web app (ESP-01) | APP-06 |  | App twist page | Set ON 3 / OFF 2 min, Save & Start; reload | Twist runs; page shows 3/2 min and running |  | Not Run
TC-APP-07 | Web app (ESP-01) | APP-07 |  | Countdown started from button 4 | Open app countdown page | Page shows remaining time counting down |  | Not Run
TC-APP-08 | Web app (ESP-01) | APP-08 |  | App settings page | Check buzzer switches and power restore | 3 separate buzzer switches; power restore ON/OFF |  | Not Run

## Decisions
ID | Topic | Current behaviour | Options | Client decision | Client Comment
DEC-01 | Timer after tank full | Now: motor restarts as soon as the level drops below 100% while the slot is active. Auto and Twist wait for 25%. | (a) Keep as now (b) Restart only at 25% or below
DEC-02 | Manual and tank full | Now: Manual does not stop at tank full (tank full is not an off key for Manual in the testing report). | (a) Keep as now (b) Stop Manual at tank full
DEC-03 | Automatic Auto when idle | Now: when no mode is running and the level falls to 50%, the device starts Auto by itself (unless the user switched Auto off). | (a) Keep as now (b) Never start Auto by itself
DEC-04 | Retry count used up | Now: after all dry run retries fail, the motor waits for ground water or the user. | (a) Keep as now (b) Retry again after a longer gap - give time
DEC-05 | Current fault recovery | Now: after an over/under-current trip the motor may restart after the testing gap (default 30 min). | (a) Keep as now (b) Different time - give time (c) Only the user restarts
DEC-06 | Starter relays | Now: relay 2 = 2 s pulse at motor start, relay 3 = 2 s pulse at motor stop. | (a) Correct (b) Different wiring - describe
DEC-07 | Twist days | Now: the app lets you pick days for Twist but the device runs Twist every day. | (a) Every day is fine (b) Add day selection